# Pre-submission sprint (now → 30.11)
## Week 1: 28.10–03.11
- Harden the Flask MVP you already have:
  - Clean routes, add basic error handling & size limits.
  - Add Tesseract OCR for a proof-of-concept on 2 doc types (Passport, Diploma).
  - Verify Berlin checklist text and wording in state_rules.py.
- Create 10–12 anonymized sample files (good/bad quality) for testing.
- Decision: deploy target (Render or Fly.io) and create project.
Deliverables: Deployed MVP (public URL), OCR PoC, Berlin checklist v1, sample test set.
## Week 2: 04.11–10.11
- Add SQLite persistence (Candidates, Uploads, Results).
- “My Cases” dashboard + simple status (Incomplete / Ready).
- Email templates (German) for missing docs (copy-paste ready).
- Deploy CI basics (lint + format) and push to GitHub.
Deliverables: Persistent cases, dashboard, email drafts, repo ready.
## Week 3: 11.11–17.11
- Expand checklists: Bavaria and NRW.
- Add analytics mini-panel (avg. missing docs, detection rate, per-state breakdown).
- Create 2-minute demo script (voiceover text + click path).
Deliverables: 3-state coverage, analytics panel, demo script.
## Week 4: 18.11–24.11
- UI polish (Bootstrap consistency, progress meter, alert copy).
- Record demo video (screen capture) + short GIF.
- Draft 1-page submission (Problem / Solution / Impact / 10× potential) and slide.
Deliverables: Final UI, video + GIF, one-pager, slide draft.
## Week 5: 25.11–29.11
- Dry-run with 10 sample cases; note accuracy and time saved.
- Add a short “Security & Privacy” note (no PHI stored; sample data only).
- Submit by 29.11 (buffer day).
Deliverables: Submission packet ready & sent (URL, video, one-pager, slide, metrics note).
## Deadline day: 30.11
Final check, resubmit if needed; post a brief summary to stakeholders.

# Submission packet (checklist)
- ✅ URL to the running Flask MVP
- ✅ 2-min demo video (walkthrough: upload → detect → missing → email template)
- ✅ One-pager (copy below)
- ✅ Slide (single slide “from paperwork to placement”)
- ✅ 90-day implementation plan (below)
- ✅ Metrics snapshot (on sample data): detection rate %, avg. missing docs, minutes saved/case

# Paste-ready one-pager (for the form)
Title: Anerkennung AI Cockpit
Problem: Anerkennung in Germany is fragmented by state. Files bounce due to missing/incorrect docs and translations, delaying onboarding by months and consuming recruiter time.
Solution: A lightweight Cockpit that (1) generates state-specific checklists, (2) analyzes uploaded docs via OCR/LLM to detect what’s present/missing, and (3) produces German email templates to request exactly what’s missing.
MVP demo: Flask app (Berlin/Bavaria/NRW), OCR PoC for Passport/Diploma, case dashboard, analytics mini-panel.
Expected impact (pilot):
- File-return rate ↓ from ~35% → <10%
- Recognition cycle time ↓ by 4–8 weeks (case-ready sooner)
- Recruiter handling time ↓ from ~10h → <2h per case
  10× potential: Add all 16 states + authority directory, then replicate framework for UAE/KSA/Japan recognition → global compliance layer for healthcare mobility.
  Actionability: MVP is deployable today; expansion plan achieves production readiness in ≤90 days.

# 90-day implementation plan (post-selection)
Phase 1 — Core Doc-AI & States (Weeks 1–3)
- Integrate robust OCR (Tesseract + heuristics or Google Document AI).
- LLM classifier for doc types; target >85% correct classification on key docs.
- Expand state coverage from 3 → 8 (add Hesse, Baden-Württemberg, Lower Saxony, Hamburg, Saxony).
- Metrics: detection precision/recall; reduce “unknown” rate <10%.
Phase 2 — Workflow & Authority Ops (Weeks 4–6)
- Authority directory (emails, forms, portals) + auto-generated authority emails.
- SLA timers & alerts; export submission bundle (PDF checklist + filenames + notes).
- Role-based access (Recruiter, Ops, Read-only).
- Metrics: % files “ready to submit”; average time to ready.
Phase 3 — Compliance & Scale (Weeks 7–9)
- Add translations & apostille checks; mark “certified” vs. “non-certified”.
- Cover all 16 states; add batch case imports from CSV/CRM.
- Privacy hardening (signed URLs, retention policy, audit log).
- Go/No-Go gates + rollout plan to German teams.
Across all phases
- Weekly accuracy reports; error triage; user feedback loop in app.
- Docs & training snippets for recruiters.